POSBUDDY

POS Field Operations Management Platform

SOFTWARE DEVELOPMENT LIFECYCLE

Master Implementation Plan

Version 1.0 | 01/03/2026

Ultimate Digital Solutions Pvt Ltd

Prepared by: Sourabh Bhaumik

# 1. Executive Summary

POSBUDDY is a multi-tenant SaaS platform for managing POS terminal field operations. It serves UDS and its customers (Hitachi, PhonePE, Fiserv, Mosambee, BonusHub, IServeU) by digitizing the entire call lifecycle: from customer data import through field engineer dispatch, on-site closure with photo/GPS capture, to report generation and download.

Architecture: Next.js 15 (App Router) + Supabase (PostgreSQL + Auth + Storage + Edge Functions) + Vercel deployment

Manpower Source: UDSHR project via pos_staff sync (project_id = UDS-POS)

Database: 12-table schema (v3.2) with EAV closure forms, column mapping engine, audit trail

Environments: Staging (Supabase project: hlkjyahgsvcytbofdnnk) then Production (separate Supabase project)

Repository: github.com/srksourabh/posbuddy.git

# 2. Technology Stack Decisions

## 2.1 Why This Stack

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 1 | Frontend Framework: Next.js 15 (App Router) | Selected | SSR + API routes in one repo, React Server Components for performance |
| 2 | Backend/DB: Supabase | Selected | PostgreSQL, Row Level Security, Auth, S3-compatible Storage, Realtime — all managed |
| 3 | Hosting: Vercel | Selected | Zero-config Next.js deploys, preview branches = staging URLs, edge functions |
| 4 | UI Library: shadcn/ui + Tailwind CSS v4 | Selected | Customizable components, accessible, modern design system, unique look |
| 5 | Mobile: PWA (Progressive Web App) | Selected | FSE field app via installable PWA — camera, GPS, offline queue. No app store needed. |
| 6 | File Storage: Supabase Storage (S3) | Selected | Photos, signatures, imported Excels, generated reports |
| 7 | Auth: Supabase Auth | Selected | Phone OTP for FSE, email/password for Back Office, JWT + RLS policies |

## 2.2 Git Branching Strategy

Three-environment branching model aligned with Vercel preview deployments:

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 1 | main branch | Production | Protected. Only merged from staging after sign-off. Deploys to production Vercel + Supabase. |
| 2 | staging branch | Staging | Integration branch. All feature branches merge here first. Vercel preview URL serves as staging. |
| 3 | feature/* branches | Development | One branch per task. Created from staging. PR reviewed before merge to staging. |
| 4 | hotfix/* branches | Emergency | Created from main for critical production fixes. Merged to both main and staging. |

# 3. Implementation Phases

| PHASE 1: PROJECT SCAFFOLDING + DATABASE | Week 1-2 |
| --- | --- |

Set up the repository structure, database schema on Supabase staging, authentication, and the base UI shell. This phase produces a deployable skeleton with working auth.

### Phase 1 Tasks

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 1.1 | Initialize Next.js 15 project with App Router, TypeScript, Tailwind CSS v4, shadcn/ui | Claude Code | Project skeleton with folder structure, tsconfig, tailwind config |
| 1.2 | Configure Supabase client (staging project already exists: hlkjyahgsvcytbofdnnk) | Claude Code | .env.local (exists), supabase client lib, types generation |
| 1.3 | Create all 12 database tables via Supabase SQL editor / migrations | Claude Code | SQL migration files in supabase/migrations/ |
| 1.4 | Seed master data: 6 customers, 10 banks, 5 call types, 6 device models | Claude Code | Seed SQL file, verified via Supabase dashboard |
| 1.5 | Set up Row Level Security (RLS) policies per access control rules in schema doc | Claude Code | RLS policies: FSE sees own calls, Back Office sees all/downline |
| 1.6 | Configure Supabase Auth: phone OTP (FSE), email/password (Back Office) | Cowork + Supabase Dashboard | Auth providers enabled, test login flows |
| 1.7 | Create base layout shell: sidebar nav, header with user context, responsive design | Claude Code | Layout components with shadcn/ui, unique UDS-branded theme |
| 1.8 | Set up Git: staging branch, branch protection rules, .gitignore, README | Cowork (Git) | Repository structured, staging branch created and pushed |
| 1.9 | Deploy skeleton to Vercel, connect staging branch as preview | Cowork + Vercel | Live staging URL accessible |
| 1.10 | Create Supabase Storage buckets: call-photos, signatures, imports, reports | Claude Code | 4 storage buckets with appropriate access policies |

Cowork Role in Phase 1: Git operations (branch creation, commits, push), Vercel deployment configuration via connected MCP, Supabase dashboard configuration, document generation for sign-off.

Claude Code Role in Phase 1: All code generation — Next.js setup, SQL migrations, RLS policies, React components, Supabase client configuration, TypeScript types.

| PHASE 2: CORE DATA ENGINE | Week 3-4 |
| --- | --- |

Build the column mapping engine and Excel import pipeline. This is the system’s backbone — it normalizes 75-94 column customer Excels into the unified calls table.

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 2.1 | Build column_mapping_versions CRUD: create/view/archive mapping versions per customer | Claude Code | Admin UI for managing mapping versions |
| 2.2 | Build customer_column_mappings editor: map source Excel headers to unified fields with transform rules | Claude Code | Drag-and-drop or form-based mapping interface |
| 2.3 | Build Excel import engine: upload Excel, read headers, apply active mapping version, validate, insert into calls | Claude Code | Server action / API route for import with progress feedback |
| 2.4 | Implement all 7 transform rules: direct copy, auto_generate, concatenate, date, datetime, default, lookup | Claude Code | Transform engine with unit tests |
| 2.5 | Build import batch tracking: import_batch_id grouping, imported_at timestamps, error rows log | Claude Code | Import history page with batch details |
| 2.6 | Build customer management CRUD: add/edit/deactivate customers | Claude Code | Customers list and detail pages |
| 2.7 | Build acquiring_banks, call_types, device_models master data CRUD | Claude Code | Master data admin pages |
| 2.8 | Pre-configure column mappings for all 6 existing customers (Hitachi, PhonePE, Fiserv, Mosambee, BonusHub, IServeU) | Cowork (data entry) | 6 complete mapping configurations ready for import |

Cowork Role in Phase 2: Data entry for initial 6 customer column mappings (tedious config work), testing imports with sample Excel files, generating test data documents.

Claude Code Role in Phase 2: All engine code — Excel parsing (SheetJS), transform pipeline, validation logic, database operations, UI components.

| PHASE 3: CALL MANAGEMENT + ASSIGNMENT | Week 5-6 |
| --- | --- |

The operational heart: viewing, filtering, assigning, and tracking calls. Back Office users manage the workflow; FSEs receive assignments.

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 3.1 | Build calls list page: filterable by state, district, city, pincode, customer, call type, status, FSE, date range | Claude Code | Calls dashboard with advanced filters, pagination |
| 3.2 | Build pos_staff sync from UDSHR: scheduled sync via Edge Function, hr_user_id bridge, reports_to_id resolution | Claude Code | Sync function + cron trigger, staff table populated |
| 3.3 | Build call assignment UI: select FSE (department=FSE only), assign single/bulk calls, record assigned_by and timestamp | Claude Code | Assignment modal with FSE picker and bulk select |
| 3.4 | Build call reassignment: transfer calls between FSEs with reason logging in call_status_log | Claude Code | Reassignment flow with audit trail |
| 3.5 | Build call detail view: full call info, assignment history, status timeline from call_status_log | Claude Code | Call detail page with timeline component |
| 3.6 | Build hierarchy-based filtering: Back Office sees calls of their downline via reports_to_id chain traversal | Claude Code | Recursive CTE query for downline, cached in session |
| 3.7 | Build call_status_log: auto-log every status change with old/new status, changed_by, reason, timestamp | Claude Code | Database trigger or application-level logging |
| 3.8 | Build dashboard: call counts by status, by customer, by region; daily/weekly trends | Claude Code | Dashboard page with charts (Recharts) |

Cowork Role in Phase 3: Notion documentation for workflow specs, testing assignment flows, generating status reports from staging data, Canva design assets for dashboard cards.

Claude Code Role in Phase 3: All feature code, database queries (including recursive CTEs for hierarchy), Supabase Edge Functions for sync, React components, chart integration.

| PHASE 4: FSE MOBILE APP (PWA) | Week 7-8 |
| --- | --- |

The field engineer’s primary tool. A PWA that loads assigned calls, renders customer-specific closure forms, captures photos/GPS/signatures, and submits closures.

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 4.1 | Build PWA manifest, service worker, install prompt, offline capability shell | Claude Code | Installable PWA with app-like experience on Android/iOS |
| 4.2 | Build FSE login: phone OTP via Supabase Auth, session persistence | Claude Code | OTP login screen, auto-redirect to call list |
| 4.3 | Build FSE call list: assigned calls only (RLS enforced), pull-to-refresh, status indicators | Claude Code | Mobile-optimized call list with status chips |
| 4.4 | Build dynamic closure form renderer: load closing_requirement_templates by customer_id, render correct fields (text, textarea, select, photo, signature, number, date) | Claude Code | Dynamic form engine that adapts per customer |
| 4.5 | Build photo capture: camera API integration, compress to max 1MB, preview before submit | Claude Code | Camera component with compression, multi-photo support |
| 4.6 | Build signature capture: canvas-based signature pad, save as PNG | Claude Code | Signature pad component |
| 4.7 | Build GPS capture: auto-record lat/long on visit-in and visit-out, show on map | Claude Code | Geolocation API integration with timestamp logging |
| 4.8 | Build closure submission: validate required fields, upload photos/signatures to Supabase Storage, create call_closures + closure_field_values records, auto-close call, write status log | Claude Code | Complete submission pipeline with validation and S3 upload |
| 4.9 | Build offline queue: store closures in IndexedDB when offline, sync when back online | Claude Code | Offline-first architecture with sync indicator |
| 4.10 | Build visit timer: auto-track visit_in_time and visit_out_time | Claude Code | Timer component that persists across app restarts |

Cowork Role in Phase 4: UI/UX wireframe generation via Canva, testing on physical devices, documenting FSE training materials as DOCX/PDF.

Claude Code Role in Phase 4: Entire PWA codebase — service worker, camera/GPS/signature APIs, dynamic form engine, offline sync, storage integration.

| PHASE 5: REPORTING + DOWNLOADS | Week 9-10 |
| --- | --- |

Generate downloadable reports: call lists as Excel, closure reports with photos as PDF, MIS dashboards, customer-specific formatted exports.

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 5.1 | Build Excel export: filtered call list download as .xlsx with all columns | Claude Code | Server-side Excel generation (ExcelJS), download endpoint |
| 5.2 | Build closure report PDF: per-call PDF with merchant details, closure fields, embedded photos, GPS map snapshot, signatures | Claude Code | PDF generation (Puppeteer or jsPDF) with photo embedding |
| 5.3 | Build bulk download: select multiple calls, generate ZIP of individual closure PDFs | Claude Code | Async ZIP generation with progress indicator |
| 5.4 | Build MIS report: monthly summary by customer, by region, by call type; SLA metrics | Claude Code | MIS dashboard page + downloadable Excel |
| 5.5 | Build customer-specific export formats: re-map unified data back to customer’s original column format for sending back | Claude Code | Reverse mapping engine using column_mapping_versions |
| 5.6 | Build report scheduling: auto-generate daily/weekly MIS and email to stakeholders | Claude Code | Supabase Edge Function cron + email integration |

Cowork Role in Phase 5: Design report templates in Canva/DOCX, validate generated reports against customer expectations, Notion documentation for report specs.

Claude Code Role in Phase 5: Excel/PDF generation engines, download APIs, reverse mapping logic, scheduled jobs.

| PHASE 6: API LAYER FOR CLIENT INTEGRATION | Week 11-12 |
| --- | --- |

Expose REST APIs so customer systems (Hitachi, Fiserv, etc.) can push calls directly and pull closure data programmatically instead of Excel import/export.

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 6.1 | Design API specification: OpenAPI 3.0 spec for all endpoints | Cowork | OpenAPI YAML spec document |
| 6.2 | Build API authentication: API key issuance per customer, rate limiting, request logging | Claude Code | API key management in customers table, middleware |
| 6.3 | Build POST /api/v1/calls: accept call creation payloads, validate against customer schema, insert | Claude Code | Call creation API with validation |
| 6.4 | Build GET /api/v1/calls/{id}/closure: return closure data with signed photo/signature URLs | Claude Code | Closure retrieval API with pre-signed S3 URLs |
| 6.5 | Build webhook system: notify customer systems on call status changes | Claude Code | Webhook registration + event dispatch |
| 6.6 | Build API documentation portal: interactive docs with try-it-out | Claude Code | Swagger UI or Redoc integrated into the app |
| 6.7 | Build API versioning strategy: /v1/ namespace, backward compatibility rules | Claude Code | Versioned route structure |

Cowork Role in Phase 6: API specification drafting, client communication documents, integration guides as DOCX.

Claude Code Role in Phase 6: All API implementation, auth middleware, webhook engine, documentation portal.

| PHASE 7: TESTING + STAGING VALIDATION | Week 13 |
| --- | --- |

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 7.1 | Unit tests: all transform rules, RLS policies, hierarchy queries, form validation | Claude Code | Jest/Vitest test suites, 80%+ coverage on core logic |
| 7.2 | Integration tests: full import-assign-close-report cycle per customer | Claude Code | Playwright E2E tests |
| 7.3 | Load testing: simulate 50 concurrent FSEs submitting closures with photos | Claude Code | k6 or Artillery load test scripts |
| 7.4 | Security audit: RLS policy verification, API key rotation, input sanitization | Cowork + Claude Code | Security checklist document + automated scans |
| 7.5 | UAT with real data: import actual customer Excels, run full workflows on staging | Cowork | UAT sign-off document |
| 7.6 | Performance optimization: query analysis, index verification, image compression tuning | Claude Code | Performance report with before/after metrics |

| PHASE 8: PRODUCTION DEPLOYMENT | Week 14 |
| --- | --- |

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 8.1 | Create production Supabase project (separate from staging) | Cowork (Supabase) | New project with production credentials |
| 8.2 | Run all migrations on production database | Claude Code | Production schema verified |
| 8.3 | Seed production master data (customers, banks, call types, device models) | Claude Code | Master data loaded |
| 8.4 | Configure production environment variables on Vercel | Cowork (Vercel) | Production .env configured |
| 8.5 | Deploy main branch to production Vercel domain | Cowork (Vercel) | Production URL live |
| 8.6 | Configure custom domain (posbuddy.udskolkata.com or similar) | Cowork (Vercel + DNS) | Custom domain active with SSL |
| 8.7 | Set up monitoring: Vercel Analytics, Supabase dashboard alerts, error tracking (Sentry) | Claude Code + Cowork | Monitoring dashboard active |
| 8.8 | Migrate staging data if applicable, or start fresh with production imports | Cowork | Production data ready |

# 4. Project Folder Structure

The following structure organizes the Next.js 15 App Router project. All code lives in the single posbuddy repository.

| Path | Purpose |
| --- | --- |
| app/(auth)/login/ | Login pages (phone OTP + email) |
| app/(dashboard)/ | Back Office layout group |
| app/(dashboard)/calls/ | Call list, detail, import pages |
| app/(dashboard)/assignments/ | Assignment and reassignment |
| app/(dashboard)/reports/ | MIS, export, download pages |
| app/(dashboard)/admin/ | Customers, mappings, master data |
| app/(dashboard)/dashboard/ | Home dashboard with charts |
| app/(fse)/ | FSE mobile layout group (PWA) |
| app/(fse)/my-calls/ | FSE assigned calls list |
| app/(fse)/closure/[callId]/ | Dynamic closure form |
| app/api/v1/ | REST API routes for clients |
| components/ui/ | shadcn/ui + custom components |
| components/forms/ | Dynamic form renderer |
| components/charts/ | Dashboard chart components |
| lib/supabase/ | Client, server, admin clients |
| lib/import-engine/ | Excel parser + transform engine |
| lib/export-engine/ | Excel/PDF report generators |
| lib/sync/ | UDSHR staff sync logic |
| supabase/migrations/ | SQL migration files (numbered) |
| supabase/seed.sql | Master data seed |
| public/manifest.json | PWA manifest |
| docs/plans/ | Implementation plans |
| docs/api/ | OpenAPI specs |

# 5. Staging vs Production Strategy

| Aspect | Staging | Production |
| --- | --- | --- |
| Supabase Project | hlkjyahgsvcytbofdnnk (existing) | New project (to be created) |
| Git Branch | staging | main |
| Vercel Deploy | Preview URL (auto per PR) | Production domain |
| Data | Test data, sample imports | Real customer data |
| Auth | Test phone numbers | Real OTP delivery |
| Storage | Test photos (auto-purge weekly) | Persistent production storage |
| Migrations | Applied first, tested | Applied after staging sign-off |
| API Keys | Test keys (limited rate) | Production keys per customer |
| Promotion | Feature tested here first | Merge staging to main after UAT |

# 6. Cowork vs Claude Code: Division of Labour

Each tool has a distinct strength. Here is the precise division for every category of work in this project:

| Work Category | Cowork | Claude Code |
| --- | --- | --- |
| Git Operations | Branch management, commits, push, PR creation, merge approvals | N/A (Cowork handles all Git) |
| Database Schema | Supabase dashboard config, backup scheduling | SQL migrations, RLS policies, seed scripts, types generation |
| UI/UX Design | Canva mockups, wireframes, brand assets, design review | shadcn/ui component code, Tailwind styling, responsive layout |
| Code Generation | N/A | All application code: pages, components, API routes, server actions, libs |
| Testing | Manual UAT, stakeholder demo, test data preparation | Unit tests, integration tests, E2E tests, load tests |
| Documentation | DOCX/PDF docs (proposals, manuals, SOPs), Notion pages, Canva presentations | Code comments, README, API docs, inline documentation |
| Deployment | Vercel dashboard config, domain setup, environment variables | Build configuration, deployment scripts, CI/CD setup |
| Data Entry | Customer column mappings, master data config, test imports | Data migration scripts, bulk operations |
| Monitoring | Alert configuration, dashboard review | Sentry setup, logging middleware, health check endpoints |
| Client Comms | Proposals, integration guides, SLA documents, email drafts | API specification (OpenAPI YAML) |
| Scheduling | Cron job configuration, task automation via n8n MCP | Edge Function code for scheduled tasks |

# 7. Unique UI Design Direction

The POSBUDDY interface will follow a "Field Operations Control Center" design language — distinct from generic SaaS dashboards. Key principles:

- Color System: Deep navy (#1B4F72) primary, teal (#117A65) for success states, amber (#F39C12) for pending/warnings, coral (#E74C3C) for urgent/overdue. White/light gray backgrounds. No generic blue-gray.

- Typography: Inter for UI, JetBrains Mono for ticket numbers and MID/TID codes. Clear hierarchy with size and weight, not color alone.

- Card-Based Layout: Every call is a card with status chip, customer badge, location tag, and urgency indicator. No dense table rows for primary views.

- Map Integration: Calls plotted on India map by state/district. FSE locations shown in real-time during active visits.

- FSE Mobile: Full-screen closure forms. Large touch targets. Camera opens instantly. Signature pad is full-width. Minimal typing required.

- Customer Branding: Each customer’s calls display their logo/color accent in the card header, making multi-customer views scannable.

# 8. Immediate Next Steps (This Session)

The following actions can be executed right now to start Phase 1:

| # | Task | Tool / Platform | Deliverable |
| --- | --- | --- | --- |
| 1 | Create staging branch from current main | Cowork (now) | staging branch pushed to origin |
| 2 | Initialize Next.js 15 project in the repo | Claude Code | Project bootstrapped with all configs |
| 3 | Write SQL migration: all 12 tables + indexes + constraints | Claude Code | Migration file ready for Supabase |
| 4 | Run migration on staging Supabase | Claude Code | Tables created and verified |
| 5 | Write seed SQL for master data | Claude Code | 6 customers, 10 banks, 5 call types, 6 models seeded |
| 6 | Commit and push to staging | Cowork (now) | Code on GitHub, Vercel preview triggered |

Regards,

Sourabh Bhaumik

Ultimate Digital Solutions Pvt Ltd | 9836719911